## Ahmad Hassan
DevOps Crash Course |  |  | Resource Name |  |  | Ahmad Hassan
|  |  | Training Start Date |  |  | 2019-08-27
|  |  | Expected End Date |  |  | 2019-09-23
Pre Requisites: Basic knowledge of AWS Services + Python/ EC2/ VPC & VPN/ S3/ Lambda/ RDS/ CLoudTrail
Topics | Sub-Topics | Expected Duration (Days) | Time Consumed (Days) | Start Date (Date) | End Date (Date) | Status (In Progress / Complete) | Reference
Introduction | What is DevOps? | 1 | 0.5 | 2019-08-28 | 2019-08-28 | Completed | https://www.youtube.com/watch?v=PxGGeNEdb3E
| What is CI/CD? | [5 empty] | https://aws.amazon.com/devops/what-is-devops/
| The need to merge development and operations (DevOps) | [5 empty] | https://enterprisersproject.com/article/2015/10/devops-case-study-rabobank-cuts-deployment-60
| Importance of DevOps in a project | [5 empty] | (https://opensource.com/business/16/6/how-devops-improves-teams
Infrastructure Provisioning | AWS Accounts and Permissions (Users, Roles etc) | 1 | 0.5 | 2019-08-28 | 2019-08-28 | Completed
| CloudFormation (Third party equivalents are: Chef, Puppet, Ansible) | 2 | 0.5 | 2019-08-29 | 2019-08-29 | Completed | https://docs.aws.amazon.com/AWSCloudFormation/latest/UserGuide/Welcome.html
| 3rd party tools (Ansible, Terraform, Chef, Puppet) Understand the usecases of each services. When to used Cloudformation vs Ansible? | [5 empty] | https://www.youtube.com/watch?v=OmRxKQHtDbY
| AWS AutoScaling and CloudWatch | 2 |  |  |  |  | https://docs.aws.amazon.com/AmazonCloudWatch/latest/monitoring/WhatIsCloudWatch.html
https://docs.aws.amazon.com/autoscaling/ec2/userguide/what-is-amazon-ec2-auto-scaling.html
| AWS SNS and SES | 1 |  |  |  |  | https://docs.aws.amazon.com/ses/latest/DeveloperGuide/Welcome.html
https://docs.aws.amazon.com/sns/latest/dg/welcome.html
CICD on AWS | Code Commit: Third party equivalent of Git) What is it, Concepts and How it works? | 1 | 0.5 | 2019-08-29 | 2019-08-29 | Completed | https://docs.aws.amazon.com/codecommit/latest/userguide/welcome.html
| Code Deploy: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 | 1 | 2019-08-30 | 2019-08-30 | Completed | https://docs.aws.amazon.com/codedeploy/latest/userguide/welcome.html
| Code Build: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 | 0.5 | 2019-09-02 | 2019-09-02 | Completed | https://docs.aws.amazon.com/codebuild/latest/userguide/welcome.html
| Code Pipeline: Third party equivalent of Docker) What is it, Concepts and How it works? | 1 | 0.5 | 2019-09-02 | 2019-09-02 | Completed | https://docs.aws.amazon.com/codepipeline/latest/userguide/welcome.html
https://aws.amazon.com/getting-started/projects/set-up-ci-cd-pipeline/
Applying CI/CD to Projects | Usage of GIT best practices | 2 |  |  |  |  | https://datasift.github.io/gitflow/IntroducingGitFlow.html
| Jenkins for building and deployment | [5 empty] | https://www.youtube.com/watch?v=p7-U1_E_j3w
| For more reference | [5 empty] | https://jenkins.io/doc/
| Unit Test Cases (Python) | [5 empty] | https://jeffknupp.com/blog/2013/12/09/improve-your-python-understanding-unit-testing/
| Scheduling and Orchestration Tool - Docker | [5 empty] | https://www.youtube.com/watch?v=lcQfQRDAMpQ
| For more reference | [5 empty] | https://docs.docker.com/get-started/
Monitoring | - Cloudwatch logging Groups - Cloudwatch agent based monitoring - KPI Definitions across services - XRay - Custom Cloudwatch Metrics | 2
Assignment : | - Consider a simple lambda function. - Create an API Gateway and Lambda that when hit, returns the message "Hello {name}, welcome to {applicationTitle}." where name is a parameter passed to this - API. applicationTitle should be picked from lambda environment variable. - Implement the CICD process for this function using AWS services. Any environment variables should be set from CloudFormation. - Show the success and failure CICD scenarios. - Document the services used, the steps performed and the results. | 3
Exercise : | - The services used need to be part of a CloudFormation script that can spin up resources in any account. - Automated unit testing can involve creating custom Lambda events - All code needs to be part of a GIT repo with efficient branching strategy including code review (merge request). - Upon merging with master, latest code needs to be deployed to higher environments automatically. | 2
| Total No. of Days: | 20
Prepared By: | Rubab Naziri
Separate section for Monitoring...Cloudwatch logging groups, cloudwatch agent base monitoring, KPI defnitaions across services, Xray, Custom Cloudwatch metrics

## Sufyan Raza
DevOps Crash Course |  |  | Resource Name |  |  | Sufyan Raza
|  |  | Training Start Date |  |  | 2019-08-27
|  |  | Expected End Date |  |  | 2019-09-23
Pre Requisites: Basic knowledge of AWS Services + Python/ EC2/ VPC & VPN/ S3/ Lambda/ RDS/ CLoudTrail
Topics | Sub-Topics | Expected Duration (Days) | Time Consumed (Days) | Start Date (Date) | End Date (Date) | Status (In Progress / Complete) | Reference
Introduction | What is DevOps? | 1 |  |  |  |  | https://www.youtube.com/watch?v=PxGGeNEdb3E
| What is CI/CD? | [5 empty] | https://aws.amazon.com/devops/what-is-devops/
| The need to merge development and operations (DevOps) | [5 empty] | https://enterprisersproject.com/article/2015/10/devops-case-study-rabobank-cuts-deployment-60
| Importance of DevOps in a project | [5 empty] | (https://opensource.com/business/16/6/how-devops-improves-teams
Infrastructure Provisioning | AWS Accounts and Permissions (Users, Roles etc) | 1
| CloudFormation (Third party equivalents are: Chef, Puppet, Ansible) | 2 |  |  |  |  | https://docs.aws.amazon.com/AWSCloudFormation/latest/UserGuide/Welcome.html
| 3rd party tools (Ansible, Terraform, Chef, Puppet) Understand the usecases of each services. When to used Cloudformation vs Ansible? | [5 empty] | https://www.youtube.com/watch?v=OmRxKQHtDbY
| AWS AutoScaling and CloudWatch | 2 |  |  |  |  | https://docs.aws.amazon.com/AmazonCloudWatch/latest/monitoring/WhatIsCloudWatch.html
https://docs.aws.amazon.com/autoscaling/ec2/userguide/what-is-amazon-ec2-auto-scaling.html
| AWS SNS and SES | 1 |  |  |  |  | https://docs.aws.amazon.com/ses/latest/DeveloperGuide/Welcome.html
https://docs.aws.amazon.com/sns/latest/dg/welcome.html
CICD on AWS | Code Commit: Third party equivalent of Git) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codecommit/latest/userguide/welcome.html
| Code Deploy: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codedeploy/latest/userguide/welcome.html
| Code Build: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codebuild/latest/userguide/welcome.html
| Code Pipeline: Third party equivalent of Docker) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codepipeline/latest/userguide/welcome.html
https://aws.amazon.com/getting-started/projects/set-up-ci-cd-pipeline/
Applying CI/CD to Projects | Usage of GIT best practices | 2 |  |  |  |  | https://datasift.github.io/gitflow/IntroducingGitFlow.html
| Jenkins for building and deployment | [5 empty] | https://www.youtube.com/watch?v=p7-U1_E_j3w
| For more reference | [5 empty] | https://jenkins.io/doc/
| Unit Test Cases (Python) | [5 empty] | https://jeffknupp.com/blog/2013/12/09/improve-your-python-understanding-unit-testing/
| Scheduling and Orchestration Tool - Docker | [5 empty] | https://www.youtube.com/watch?v=lcQfQRDAMpQ
| For more reference | [5 empty] | https://docs.docker.com/get-started/
Monitoring | - Cloudwatch logging Groups - Cloudwatch agent based monitoring - KPI Definitions across services - XRay - Custom Cloudwatch Metrics | 2
Assignment : | - Consider a simple lambda function. - Create an API Gateway and Lambda that when hit, returns the message "Hello {name}, welcome to {applicationTitle}." where name is a parameter passed to this - API. applicationTitle should be picked from lambda environment variable. - Implement the CICD process for this function using AWS services. Any environment variables should be set from CloudFormation. - Show the success and failure CICD scenarios. - Document the services used, the steps performed and the results. | 3
Exercise : | - The services used need to be part of a CloudFormation script that can spin up resources in any account. - Automated unit testing can involve creating custom Lambda events - All code needs to be part of a GIT repo with efficient branching strategy including code review (merge request). - Upon merging with master, latest code needs to be deployed to higher environments automatically. | 2
| Total No. of Days: | 20
Prepared By: | Rubab Naziri
Separate section for Monitoring...Cloudwatch logging groups, cloudwatch agent base monitoring, KPI defnitaions across services, Xray, Custom Cloudwatch metrics

## CloudFormationCodePipeline Exce
|  |  | Abdul Wahid |  | Abdul Haleem |  | Muneeb ur Rehman |  | Shaheryar |  | Adeel Ahmed Zeerak |  | Ahmad Hassan |  | Sufyan Raza |  | Tayyaba Younas |  | Zahra Tariq
|  |  | Time Started | Time Finished | Time Started | Time Finished | Time Started | Time Finished | Time Started | Time Finished | Time Started | Time Finished | Time Started | Time Finished | Time Started | Time Finished | Time Started | Time Finished | Time Started | Time Finished
Prequisites (30 minutes)
1 | Download CloudFormation Template: https://github.com/awslabs/aws-cloudformation-templates/blob/master/aws/services/S3/S3_Website_Bucket_With_Retain_On_Delete.yaml | Update the above template to include a parameter for the Bucket Name, make sure that the bucket is deployed with that name. Also update it to not deploy a public bucket since I think that you guys do not have that access Also, use Delete instead of Retain for DeletionPolicy...will save you a minute or two per stack deletion. | 12:00 | 12:30 | 12:00 | 12:30 | 12::00 PM | 12:30 | 12::00 PM | 12:30 | 12:00 P.M. | 12:30 P.M. | 12:15 | 13:45 | 12:00 | 12:30
Create a parameters file for the template and then use AWS CLI to deploy the template. Delete your stack once you have tested this.
2 | Code commit repository with the CloudFormation Template, the one you downloaded and updated, and accompanying parameters file.
3 | A S3 bucket named as "YOURNAME-infrastructure-scripts"
Task# | Task | SubTasks
1 (30 minutes) | From the AWS Console create a CodePipeline that | Reads source from code commit | 12:30 | 1:24 | 12:30 | 13:33 | 12:30 | 1:45 | 12:30 | 1:20 | 12:30 P.M. | 1:34 P.M. | 13:45 | 14:30 | 12:30 | 13:00 | 12.30 pm | 2.20 pm | 12:30 | 2:20
Reads a cloudformation template from the source
Deploys the template through CodeBuild (This is essentially the same as deploying using AWS CLI, except that you are using CodeBuild instead of your local system, you already have this covered from the prerequisites)
2 (60 minutes) | Create a CloudFormation Template that deploys the CodePipeline in Task#1 | Using AWS CLI, Deploy your template and verify that the CodePipeline is deployed correctly and executes successfully Note that now your BuildSpec file will have to be stored somewhere since this is an automated deployment. Put it in the same repository as your S3 CloudFormation Template. | 1:24:00 AM (lunch break) | 4:20 | 1:45-2:02 (Lunch) | 16:30 | 1:45 --- 2:15 (Lunch + Namaz) 2:15 | 16:25 | 1:20 - 1:50 (Namaz+Lunch Break) | 4:20 | 1:35 P.M. | Lunch Break (1:45 -- 2:00) 4:26 P.M. | 14:30 | 15:45 | 1:50 PM 25 mints with shumais role 25 mints lunch | 15:47 | 2:50:00 PM 2:20pm-2:50pm (Lunch-Namaz break) | 16:10 | 2:50 | 4:20
3 (80 minutes) | Create a CloudFormation Template that deploys a CodePipline to achieve the following (Create a copy of the template created in Task#1 and build upon it) | Read source from code commit | 2019-04-25 | 8 50 | 16:40 | 20:50 | 4:25 | 8:50 | 4:30 | 8:20 | 4:27 P.M. | 8:55 P.M. | 15:45 | 21:00 | 16:00 |  | 17:38 | 9 | 5:38 | 9 including namaz break
Read a cloudformation template from the source
Packages the template using CodeBuild and OUTPUTS to the bucket that you created in the prerequisites
Deploy the template using a Deploy action with CloudFormation as a provider. Keep in mind that a packaged template has already been uploaded to S3 in the last stage by CodeBuild, maybe we can reuse it.
4 (60 minutes) | Create a CloudFormation Template that deploys a CodePipline to achieve the following (Create a copy of the template created in Task#1 or Task#2 and build upon it, by now you should have a good idea about which one to use) | Read source from code commit | 9 00 | 10 50 | 21:00 | 23:00 | 8:50 | 10:50 | 8:30 | 10:20 | 8:56 P.M. | 11:00 P.M. | 21:00 | 22:30 |  |  | 10:15 | 11:17 | 10:15 | 11:16
Read a cloudformation template from the source
Packages the template using CodeBuild and OUTPUTS to the bucket that you created in the prerequisites
Creates a ChangeSet using CloudFormation
Executes a ChangeSet using CloudFormation
Note: There will be three stacks deployed one each for Task#s 2, 3 and 4. So each stack will obviously be deploying a bucket that is uniquely named becausel of the global naming constraint.. For the second Stack, your parameter file should be able to take care of the name of the first bucket For the third and fourth stack you will still use the parameter file, as in task#2, but you will override the parameter value at runtime using ParameterOverrides

## Adeel Ahmed Zeerak
DevOps Crash Course |  |  | Resource Name |  |  | Adeel Ahmed Zeerak
|  |  | Training Start Date |  |  | 2019-08-27
|  |  | Expected End Date |  |  | 2019-09-23
Pre Requisites: Basic knowledge of AWS Services + Python/ EC2/ VPC & VPN/ S3/ Lambda/ RDS/ CLoudTrail
Topics | Sub-Topics | Expected Duration (Days) | Time Consumed (Days) | Start Date (Date) | End Date (Date) | Status (In Progress / Complete) | Reference
Introduction | What is DevOps? | 1 |  |  |  |  | https://www.youtube.com/watch?v=PxGGeNEdb3E
| What is CI/CD? | [5 empty] | https://aws.amazon.com/devops/what-is-devops/
| The need to merge development and operations (DevOps) | [5 empty] | https://enterprisersproject.com/article/2015/10/devops-case-study-rabobank-cuts-deployment-60
| Importance of DevOps in a project | [5 empty] | (https://opensource.com/business/16/6/how-devops-improves-teams
Infrastructure Provisioning | AWS Accounts and Permissions (Users, Roles etc) | 1
| CloudFormation (Third party equivalents are: Chef, Puppet, Ansible) | 2 |  |  |  |  | https://docs.aws.amazon.com/AWSCloudFormation/latest/UserGuide/Welcome.html
| 3rd party tools (Ansible, Terraform, Chef, Puppet) Understand the usecases of each services. When to used Cloudformation vs Ansible? | [5 empty] | https://www.youtube.com/watch?v=OmRxKQHtDbY
| AWS AutoScaling and CloudWatch | 2 |  |  |  |  | https://docs.aws.amazon.com/AmazonCloudWatch/latest/monitoring/WhatIsCloudWatch.html
https://docs.aws.amazon.com/autoscaling/ec2/userguide/what-is-amazon-ec2-auto-scaling.html
| AWS SNS and SES | 1 |  |  |  |  | https://docs.aws.amazon.com/ses/latest/DeveloperGuide/Welcome.html
https://docs.aws.amazon.com/sns/latest/dg/welcome.html
CICD on AWS | Code Commit: Third party equivalent of Git) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codecommit/latest/userguide/welcome.html
| Code Deploy: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codedeploy/latest/userguide/welcome.html
| Code Build: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codebuild/latest/userguide/welcome.html
| Code Pipeline: Third party equivalent of Docker) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codepipeline/latest/userguide/welcome.html
https://aws.amazon.com/getting-started/projects/set-up-ci-cd-pipeline/
Applying CI/CD to Projects | Usage of GIT best practices | 2 |  |  |  |  | https://datasift.github.io/gitflow/IntroducingGitFlow.html
| Jenkins for building and deployment | [5 empty] | https://www.youtube.com/watch?v=p7-U1_E_j3w
| For more reference | [5 empty] | https://jenkins.io/doc/
| Unit Test Cases (Python) | [5 empty] | https://jeffknupp.com/blog/2013/12/09/improve-your-python-understanding-unit-testing/
| Scheduling and Orchestration Tool - Docker | [5 empty] | https://www.youtube.com/watch?v=lcQfQRDAMpQ
| For more reference | [5 empty] | https://docs.docker.com/get-started/
Monitoring | - Cloudwatch logging Groups - Cloudwatch agent based monitoring - KPI Definitions across services - XRay - Custom Cloudwatch Metrics | 2
Assignment : | - Consider a simple lambda function. - Create an API Gateway and Lambda that when hit, returns the message "Hello {name}, welcome to {applicationTitle}." where name is a parameter passed to this - API. applicationTitle should be picked from lambda environment variable. - Implement the CICD process for this function using AWS services. Any environment variables should be set from CloudFormation. - Show the success and failure CICD scenarios. - Document the services used, the steps performed and the results. | 3
Exercise : | - The services used need to be part of a CloudFormation script that can spin up resources in any account. - Automated unit testing can involve creating custom Lambda events - All code needs to be part of a GIT repo with efficient branching strategy including code review (merge request). - Upon merging with master, latest code needs to be deployed to higher environments automatically. | 2
| Total No. of Days: | 20
Prepared By: | Rubab Naziri
Separate section for Monitoring...Cloudwatch logging groups, cloudwatch agent base monitoring, KPI defnitaions across services, Xray, Custom Cloudwatch metrics

## Tayyaba Younas
DevOps Crash Course |  |  | Resource Name |  |  | Tayyaba Younas
|  |  | Training Start Date |  |  | 2019-08-27
|  |  | Expected End Date |  |  | 2019-09-23
Pre Requisites: Basic knowledge of AWS Services + Python/ EC2/ VPC & VPN/ S3/ Lambda/ RDS/ CLoudTrail
Topics | Sub-Topics | Expected Duration (Days) | Time Consumed (Days) | Start Date (Date) | End Date (Date) | Status (In Progress / Complete) | Reference
Introduction | What is DevOps? | 1 |  |  |  |  | https://www.youtube.com/watch?v=PxGGeNEdb3E
| What is CI/CD? | [5 empty] | https://aws.amazon.com/devops/what-is-devops/
| The need to merge development and operations (DevOps) | [5 empty] | https://enterprisersproject.com/article/2015/10/devops-case-study-rabobank-cuts-deployment-60
| Importance of DevOps in a project | [5 empty] | (https://opensource.com/business/16/6/how-devops-improves-teams
Infrastructure Provisioning | AWS Accounts and Permissions (Users, Roles etc) | 1
| CloudFormation (Third party equivalents are: Chef, Puppet, Ansible) | 2 |  |  |  |  | https://docs.aws.amazon.com/AWSCloudFormation/latest/UserGuide/Welcome.html
| 3rd party tools (Ansible, Terraform, Chef, Puppet) Understand the usecases of each services. When to used Cloudformation vs Ansible? | [5 empty] | https://www.youtube.com/watch?v=OmRxKQHtDbY
| AWS AutoScaling and CloudWatch | 2 |  |  |  |  | https://docs.aws.amazon.com/AmazonCloudWatch/latest/monitoring/WhatIsCloudWatch.html
https://docs.aws.amazon.com/autoscaling/ec2/userguide/what-is-amazon-ec2-auto-scaling.html
| AWS SNS and SES | 1 |  |  |  |  | https://docs.aws.amazon.com/ses/latest/DeveloperGuide/Welcome.html
https://docs.aws.amazon.com/sns/latest/dg/welcome.html
CICD on AWS | Code Commit: Third party equivalent of Git) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codecommit/latest/userguide/welcome.html
| Code Deploy: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codedeploy/latest/userguide/welcome.html
| Code Build: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codebuild/latest/userguide/welcome.html
| Code Pipeline: Third party equivalent of Docker) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codepipeline/latest/userguide/welcome.html
https://aws.amazon.com/getting-started/projects/set-up-ci-cd-pipeline/
Applying CI/CD to Projects | Usage of GIT best practices | 2 |  |  |  |  | https://datasift.github.io/gitflow/IntroducingGitFlow.html
| Jenkins for building and deployment | [5 empty] | https://www.youtube.com/watch?v=p7-U1_E_j3w
| For more reference | [5 empty] | https://jenkins.io/doc/
| Unit Test Cases (Python) | [5 empty] | https://jeffknupp.com/blog/2013/12/09/improve-your-python-understanding-unit-testing/
| Scheduling and Orchestration Tool - Docker | [5 empty] | https://www.youtube.com/watch?v=lcQfQRDAMpQ
| For more reference | [5 empty] | https://docs.docker.com/get-started/
Monitoring | - Cloudwatch logging Groups - Cloudwatch agent based monitoring - KPI Definitions across services - XRay - Custom Cloudwatch Metrics | 2
Assignment : | - Consider a simple lambda function. - Create an API Gateway and Lambda that when hit, returns the message "Hello {name}, welcome to {applicationTitle}." where name is a parameter passed to this - API. applicationTitle should be picked from lambda environment variable. - Implement the CICD process for this function using AWS services. Any environment variables should be set from CloudFormation. - Show the success and failure CICD scenarios. - Document the services used, the steps performed and the results. | 3
Exercise : | - The services used need to be part of a CloudFormation script that can spin up resources in any account. - Automated unit testing can involve creating custom Lambda events - All code needs to be part of a GIT repo with efficient branching strategy including code review (merge request). - Upon merging with master, latest code needs to be deployed to higher environments automatically. | 2
| Total No. of Days: | 20
Prepared By: | Rubab Naziri
Separate section for Monitoring...Cloudwatch logging groups, cloudwatch agent base monitoring, KPI defnitaions across services, Xray, Custom Cloudwatch metrics

## Zahra Tariq
DevOps Crash Course |  |  | Resource Name |  |  | Zahra Tariq
|  |  | Training Start Date |  |  | 2019-08-27
|  |  | Expected End Date |  |  | 2019-09-23
Pre Requisites: Basic knowledge of AWS Services + Python/ EC2/ VPC & VPN/ S3/ Lambda/ RDS/ CLoudTrail
Topics | Sub-Topics | Expected Duration (Days) | Time Consumed (Days) | Start Date (Date) | End Date (Date) | Status (In Progress / Complete) | Reference
Introduction | What is DevOps? | 1 | 1 |  |  |  | https://www.youtube.com/watch?v=PxGGeNEdb3E
| What is CI/CD? | [5 empty] | https://aws.amazon.com/devops/what-is-devops/
| The need to merge development and operations (DevOps) | [5 empty] | https://enterprisersproject.com/article/2015/10/devops-case-study-rabobank-cuts-deployment-60
| Importance of DevOps in a project | [5 empty] | (https://opensource.com/business/16/6/how-devops-improves-teams
Infrastructure Provisioning | AWS Accounts and Permissions (Users, Roles etc) | 1
| CloudFormation (Third party equivalents are: Chef, Puppet, Ansible) | 2 |  |  |  |  | https://docs.aws.amazon.com/AWSCloudFormation/latest/UserGuide/Welcome.html
| 3rd party tools (Ansible, Terraform, Chef, Puppet) Understand the usecases of each services. When to used Cloudformation vs Ansible? | [5 empty] | https://www.youtube.com/watch?v=OmRxKQHtDbY
| AWS AutoScaling and CloudWatch | 2 |  |  |  |  | https://docs.aws.amazon.com/AmazonCloudWatch/latest/monitoring/WhatIsCloudWatch.html
https://docs.aws.amazon.com/autoscaling/ec2/userguide/what-is-amazon-ec2-auto-scaling.html
| AWS SNS and SES | 1 |  |  |  |  | https://docs.aws.amazon.com/ses/latest/DeveloperGuide/Welcome.html
https://docs.aws.amazon.com/sns/latest/dg/welcome.html
CICD on AWS | Code Commit: Third party equivalent of Git) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codecommit/latest/userguide/welcome.html
| Code Deploy: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codedeploy/latest/userguide/welcome.html
| Code Build: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codebuild/latest/userguide/welcome.html
| Code Pipeline: Third party equivalent of Docker) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codepipeline/latest/userguide/welcome.html
https://aws.amazon.com/getting-started/projects/set-up-ci-cd-pipeline/
Applying CI/CD to Projects | Usage of GIT best practices | 2 |  |  |  |  | https://datasift.github.io/gitflow/IntroducingGitFlow.html
| Jenkins for building and deployment | [5 empty] | https://www.youtube.com/watch?v=p7-U1_E_j3w
| For more reference | [5 empty] | https://jenkins.io/doc/
| Unit Test Cases (Python) | [5 empty] | https://jeffknupp.com/blog/2013/12/09/improve-your-python-understanding-unit-testing/
| Scheduling and Orchestration Tool - Docker | [5 empty] | https://www.youtube.com/watch?v=lcQfQRDAMpQ
| For more reference | [5 empty] | https://docs.docker.com/get-started/
Monitoring | - Cloudwatch logging Groups - Cloudwatch agent based monitoring - KPI Definitions across services - XRay - Custom Cloudwatch Metrics | 2
Assignment : | - Consider a simple lambda function. - Create an API Gateway and Lambda that when hit, returns the message "Hello {name}, welcome to {applicationTitle}." where name is a parameter passed to this - API. applicationTitle should be picked from lambda environment variable. - Implement the CICD process for this function using AWS services. Any environment variables should be set from CloudFormation. - Show the success and failure CICD scenarios. - Document the services used, the steps performed and the results. | 3
Exercise : | - The services used need to be part of a CloudFormation script that can spin up resources in any account. - Automated unit testing can involve creating custom Lambda events - All code needs to be part of a GIT repo with efficient branching strategy including code review (merge request). - Upon merging with master, latest code needs to be deployed to higher environments automatically. | 2
| Total No. of Days: | 20
Prepared By: | Rubab Naziri
Separate section for Monitoring...Cloudwatch logging groups, cloudwatch agent base monitoring, KPI defnitaions across services, Xray, Custom Cloudwatch metrics

## Abdul Haleem
DevOps Crash Course |  |  | Resource Name |  |  | Abdul Haleem
|  |  | Training Start Date |  |  | 2019-08-20
|  |  | Expected End Date |  |  | 2019-09-16
Pre Requisites: Basic knowledge of AWS Services + Python/ EC2/ VPC & VPN/ S3/ Lambda/ RDS/ CLoudTrail
Topics | Sub-Topics | Expected Duration (Days) | Time Consumed (Days) | Start Date (Date) | End Date (Date) | Status (In Progress / Complete) | Reference
Introduction | What is DevOps? | 1 | 0.5 | 2019-08-21 | 2019-08-21 | Complete | https://www.youtube.com/watch?v=PxGGeNEdb3E
| What is CI/CD? | [5 empty] | https://aws.amazon.com/devops/what-is-devops/
| The need to merge development and operations (DevOps) | [5 empty] | https://enterprisersproject.com/article/2015/10/devops-case-study-rabobank-cuts-deployment-60
| Importance of DevOps in a project | [5 empty] | (https://opensource.com/business/16/6/how-devops-improves-teams
Infrastructure Provisioning | AWS Accounts and Permissions (Users, Roles etc) | 1 | 0.5 | 2019-08-21 | 2019-08-21 | Complete
| CloudFormation (Third party equivalents are: Chef, Puppet, Ansible) | 2 | 2 | 2019-08-22 | 2019-08-23 | Complete | https://docs.aws.amazon.com/AWSCloudFormation/latest/UserGuide/Welcome.html
| 3rd party tools (Ansible, Terraform, Chef, Puppet) Understand the usecases of each services. When to used Cloudformation vs Ansible? | [5 empty] | https://www.youtube.com/watch?v=OmRxKQHtDbY
| AWS AutoScaling and CloudWatch | 2 | 3 | 2019-08-26 | 2019-08-28 | Complete | https://docs.aws.amazon.com/AmazonCloudWatch/latest/monitoring/WhatIsCloudWatch.html
https://docs.aws.amazon.com/autoscaling/ec2/userguide/what-is-amazon-ec2-auto-scaling.html
| AWS SNS and SES | 1 | 0.5 | 2019-08-29 | 2019-08-29 | Complete | https://docs.aws.amazon.com/ses/latest/DeveloperGuide/Welcome.html
https://docs.aws.amazon.com/sns/latest/dg/welcome.html
CICD on AWS | Code Commit: Third party equivalent of Git) What is it, Concepts and How it works? | 1 | 0.5 | 2019-08-29 | 2019-08-29 | Complete | https://docs.aws.amazon.com/codecommit/latest/userguide/welcome.html
| Code Deploy: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 | 1 | 2019-08-30 | 2019-08-30 | Complete | https://docs.aws.amazon.com/codedeploy/latest/userguide/welcome.html
| Code Build: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codebuild/latest/userguide/welcome.html
| Code Pipeline: Third party equivalent of Docker) What is it, Concepts and How it works? | 1 |  |  |  |  | https://docs.aws.amazon.com/codepipeline/latest/userguide/welcome.html
https://aws.amazon.com/getting-started/projects/set-up-ci-cd-pipeline/
Applying CI/CD to Projects | Usage of GIT best practices | 2 |  |  |  |  | https://datasift.github.io/gitflow/IntroducingGitFlow.html
| Jenkins for building and deployment | [5 empty] | https://www.youtube.com/watch?v=p7-U1_E_j3w
| For more reference | [5 empty] | https://jenkins.io/doc/
| Unit Test Cases (Python) | [5 empty] | https://jeffknupp.com/blog/2013/12/09/improve-your-python-understanding-unit-testing/
| Scheduling and Orchestration Tool - Docker | [5 empty] | https://www.youtube.com/watch?v=lcQfQRDAMpQ
| For more reference | [5 empty] | https://docs.docker.com/get-started/
Monitoring | - Cloudwatch logging Groups - Cloudwatch agent based monitoring - KPI Definitions across services - XRay - Custom Cloudwatch Metrics | 2
Assignment : | - Consider a simple lambda function. - Create an API Gateway and Lambda that when hit, returns the message "Hello {name}, welcome to {applicationTitle}." where name is a parameter passed to this - API. applicationTitle should be picked from lambda environment variable. - Implement the CICD process for this function using AWS services. Any environment variables should be set from CloudFormation. - Show the success and failure CICD scenarios. - Document the services used, the steps performed and the results. | 3
Exercise : | - The services used need to be part of a CloudFormation script that can spin up resources in any account. - Automated unit testing can involve creating custom Lambda events - All code needs to be part of a GIT repo with efficient branching strategy including code review (merge request). - Upon merging with master, latest code needs to be deployed to higher environments automatically. | 2
| Total No. of Days: | 20
Prepared By: | Rubab Naziri
Separate section for Monitoring...Cloudwatch logging groups, cloudwatch agent base monitoring, KPI defnitaions across services, Xray, Custom Cloudwatch metrics

## Abdul Wahid
DevOps Crash Course |  |  | Resource Name | Abdul Wahid
|  |  | Training Start Date | 2019-08-20
|  |  | Expected End Date | 2019-09-16
Pre Requisites: Basic knowledge of AWS Services + Python/ EC2/ VPC & VPN/ S3/ Lambda/ RDS/ CLoudTrail
Topics | Sub-Topics | Expected Duration (Days) | Expected Duration (Days) | Start Date (Date) | End Date (Date) | Status (In Progress / Complete) | Reference
Introduction | What is DevOps? | 1 | 1 | 2019-08-20 | 2019-08-20 | Complete | https://www.youtube.com/watch?v=PxGGeNEdb3E
| What is CI/CD? | [5 empty] | https://aws.amazon.com/devops/what-is-devops/
| The need to merge development and operations (DevOps) | [5 empty] | https://enterprisersproject.com/article/2015/10/devops-case-study-rabobank-cuts-deployment-60
| Importance of DevOps in a project | [5 empty] | (https://opensource.com/business/16/6/how-devops-improves-teams
Infrastructure Provisioning | AWS Accounts and Permissions (Users, Roles etc) | 1 | 1 | 2019-08-21 | 2019-08-21 | Complete
| CloudFormation (Third party equivalents are: Chef, Puppet, Ansible) | 2 | 2 | 2019-08-21 | 2019-08-23 | Complete | https://docs.aws.amazon.com/AWSCloudFormation/latest/UserGuide/Welcome.html
| 3rd party tools (Ansible, Terraform, Chef, Puppet) Understand the usecases of each services. When to used Cloudformation vs Ansible? | [5 empty] | https://www.youtube.com/watch?v=OmRxKQHtDbY
| AWS AutoScaling and CloudWatch | 2 | 3 | 2019-08-26 | 2019-08-28 | Complete | https://docs.aws.amazon.com/AmazonCloudWatch/latest/monitoring/WhatIsCloudWatch.html
https://docs.aws.amazon.com/autoscaling/ec2/userguide/what-is-amazon-ec2-auto-scaling.html
| AWS SNS and SES | 1 | 0.5 | 2019-08-29 | 2019-08-29 | Complete | https://docs.aws.amazon.com/ses/latest/DeveloperGuide/Welcome.html
https://docs.aws.amazon.com/sns/latest/dg/welcome.html
CICD on AWS | Code Commit: Third party equivalent of Git) What is it, Concepts and How it works? | 1 | 0.5 | 2019-08-29 | 2019-08-29 | Complete | https://docs.aws.amazon.com/codecommit/latest/userguide/welcome.html
| Code Deploy: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 | 1 | 2019-08-30 | 2019-08-30 | Complete | https://docs.aws.amazon.com/codedeploy/latest/userguide/welcome.html
| Code Build: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 | 1 | 2019-09-02 | 2019-09-02 | Complete | https://docs.aws.amazon.com/codebuild/latest/userguide/welcome.html
| Code Pipeline: Third party equivalent of Docker) What is it, Concepts and How it works? | 1 | 1 | 2019-09-02 | 2019-09-03 | Complete | https://docs.aws.amazon.com/codepipeline/latest/userguide/welcome.html
https://aws.amazon.com/getting-started/projects/set-up-ci-cd-pipeline/
Applying CI/CD to Projects | Usage of GIT best practices | 2 |  |  |  |  | https://datasift.github.io/gitflow/IntroducingGitFlow.html
| Jenkins for building and deployment | [5 empty] | https://www.youtube.com/watch?v=p7-U1_E_j3w
| For more reference | [5 empty] | https://jenkins.io/doc/
| Unit Test Cases (Python) | [5 empty] | https://jeffknupp.com/blog/2013/12/09/improve-your-python-understanding-unit-testing/
| Scheduling and Orchestration Tool - Docker | [5 empty] | https://www.youtube.com/watch?v=lcQfQRDAMpQ
| For more reference | [5 empty] | https://docs.docker.com/get-started/
Monitoring | - Cloudwatch logging Groups - Cloudwatch agent based monitoring - KPI Definitions across services - XRay - Custom Cloudwatch Metrics | 2
Assignment : | - Consider a simple lambda function. - Create an API Gateway and Lambda that when hit, returns the message "Hello {name}, welcome to {applicationTitle}." where name is a parameter passed to this API. applicationTitle should be picked from lambda environment variable. - Implement the CICD process for this function using AWS services. Any environment variables should be set from CloudFormation. - Show the success and failure CICD scenarios. - Document the services used, the steps performed and the results. | 3
Exercise : | - The services used need to be part of a CloudFormation script that can spin up resources in any account. - Automated unit testing can involve creating custom Lambda events - All code needs to be part of a GIT repo with efficient branching strategy including code review (merge request). - Upon merging with master, latest code needs to be deployed to higher environments automatically. | 2
| Total No. of Days: | 20
Prepared By: | Rubab Naziri
Separate section for Monitoring...Cloudwatch logging groups, cloudwatch agent base monitoring, KPI defnitaions across services, Xray, Custom Cloudwatch metrics

## Danial Ahmed
DevOps Crash Course |  |  | Resource Name | Danial Ahmed
|  |  | Training Start Date | 2019-08-06
|  |  | Expected End Date | 2019-09-06
Pre Requisites: Basic knowledge of AWS Services + Python/ EC2/ VPC & VPN/ S3/ Lambda/ RDS/ CLoudTrail
Topics | Sub-Topics | Expected Duration (Days) | Time Consumed (Days) | Status (In Progress / Complete) | Reference | Start Date | End Date
Introduction | What is DevOps? | 1 | 1 | Complete | https://www.youtube.com/watch?v=PxGGeNEdb3E | 2019-08-20 | 20
| What is CI/CD? |  |  |  | https://aws.amazon.com/devops/what-is-devops/
| The need to merge development and operations (DevOps) |  |  |  | https://enterprisersproject.com/article/2015/10/devops-case-study-rabobank-cuts-deployment-60
| Importance of DevOps in a project |  |  |  | (https://opensource.com/business/16/6/how-devops-improves-teams
Infrastructure Provisioning | AWS Accounts and Permissions (Users, Roles etc) | 1
| CloudFormation (Third party equivalents are: Chef, Puppet, Ansible) | 2 |  |  | https://docs.aws.amazon.com/AWSCloudFormation/latest/UserGuide/Welcome.html
| 3rd party tools (Ansible, Terraform, Chef, Puppet) Understand the usecases of each services. When to used Cloudformation vs Ansible? |  |  |  | https://www.youtube.com/watch?v=OmRxKQHtDbY
| AWS AutoScaling and CloudWatch | 2 |  |  | https://docs.aws.amazon.com/AmazonCloudWatch/latest/monitoring/WhatIsCloudWatch.html
https://docs.aws.amazon.com/autoscaling/ec2/userguide/what-is-amazon-ec2-auto-scaling.html
| AWS SNS and SES | 1 |  |  | https://docs.aws.amazon.com/ses/latest/DeveloperGuide/Welcome.html
https://docs.aws.amazon.com/sns/latest/dg/welcome.html
CICD on AWS | Code Commit: Third party equivalent of Git) What is it, Concepts and How it works? | 1 |  |  | https://docs.aws.amazon.com/codecommit/latest/userguide/welcome.html
| Code Deploy: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 |  |  | https://docs.aws.amazon.com/codedeploy/latest/userguide/welcome.html
| Code Build: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 |  |  | https://docs.aws.amazon.com/codebuild/latest/userguide/welcome.html
| Code Pipeline: Third party equivalent of Docker) What is it, Concepts and How it works? | 1 |  |  | https://docs.aws.amazon.com/codepipeline/latest/userguide/welcome.html
https://aws.amazon.com/getting-started/projects/set-up-ci-cd-pipeline/
Applying CI/CD to Projects | Usage of GIT best practices | 2 |  |  | https://datasift.github.io/gitflow/IntroducingGitFlow.html
| Jenkins for building and deployment |  |  |  | https://www.youtube.com/watch?v=p7-U1_E_j3w
| For more reference |  |  |  | https://jenkins.io/doc/
| Unit Test Cases (Python) |  |  |  | https://jeffknupp.com/blog/2013/12/09/improve-your-python-understanding-unit-testing/
| Scheduling and Orchestration Tool - Docker |  |  |  | https://www.youtube.com/watch?v=lcQfQRDAMpQ
| For more reference |  |  |  | https://docs.docker.com/get-started/
Monitoring | - Cloudwatch logging Groups - Cloudwatch agent based monitoring - KPI Definitions across services - XRay - Custom Cloudwatch Metrics | 2
Assignment : | - Consider a simple lambda function. - Create an API Gateway and Lambda that when hit, returns the message "Hello {name}, welcome to {applicationTitle}." where name is a parameter passed to this API. applicationTitle should be picked from lambda environment variable. - Implement the CICD process for this function using AWS services. Any environment variables should be set from CloudFormation. - Show the success and failure CICD scenarios. - Document the services used, the steps performed and the results. | 3
Exercise : | - The services used need to be part of a CloudFormation script that can spin up resources in any account. - Automated unit testing can involve creating custom Lambda events - All code needs to be part of a GIT repo with efficient branching strategy including code review (merge request). - Upon merging with master, latest code needs to be deployed to higher environments automatically. | 2
| Total No. of Days: | 20
Prepared By: | Rubab Naziri
Separate section for Monitoring...Cloudwatch logging groups, cloudwatch agent base monitoring, KPI defnitaions across services, Xray, Custom Cloudwatch metrics

## Muneeb Ur Rehman
DevOps Crash Course |  |  | Resource Name | Muneeb Ur Rehman
|  |  | Training Start Date | 2019-08-20
|  |  | Expected End Date | 2019-09-20
Pre Requisites: Basic knowledge of AWS Services + Python/ EC2/ VPC & VPN/ S3/ Lambda/ RDS/ CLoudTrail
Topics | Sub-Topics | Expected Duration (Days) | Time Consumed (Days) | Status (In Progress / Complete) | Reference | Start Date | End Date
Introduction | What is DevOps? | 1 | 1 | Complete | https://www.youtube.com/watch?v=PxGGeNEdb3E | 2019-08-20 | 2019-08-20
| What is CI/CD? |  |  |  | https://aws.amazon.com/devops/what-is-devops/
| The need to merge development and operations (DevOps) |  |  |  | https://enterprisersproject.com/article/2015/10/devops-case-study-rabobank-cuts-deployment-60
| Importance of DevOps in a project |  |  |  | (https://opensource.com/business/16/6/how-devops-improves-teams
Infrastructure Provisioning | AWS Accounts and Permissions (Users, Roles etc) | 1 | 1 | Complete |  | 2019-08-21 | 2019-08-21
| CloudFormation (Third party equivalents are: Chef, Puppet, Ansible) | 2 | 2 | Complete | https://docs.aws.amazon.com/AWSCloudFormation/latest/UserGuide/Welcome.html
| 3rd party tools (Ansible, Terraform, Chef, Puppet) Understand the usecases of each services. When to used Cloudformation vs Ansible? |  |  |  | https://www.youtube.com/watch?v=OmRxKQHtDbY | 2019-08-22 | 2019-08-23
| AWS AutoScaling and CloudWatch | 2 | 2.5 | Complete | https://docs.aws.amazon.com/AmazonCloudWatch/latest/monitoring/WhatIsCloudWatch.html
[5 empty] | https://docs.aws.amazon.com/autoscaling/ec2/userguide/what-is-amazon-ec2-auto-scaling.html | 2019-08-26 | 2019-08-28
| AWS SNS and SES | 1 | 1 | Complete | https://docs.aws.amazon.com/ses/latest/DeveloperGuide/Welcome.html
[5 empty] | https://docs.aws.amazon.com/sns/latest/dg/welcome.html | 2019-08-27 | 2019-08-29
CICD on AWS | Code Commit: Third party equivalent of Git) What is it, Concepts and How it works? | 1 | 0.5 | Complete | https://docs.aws.amazon.com/codecommit/latest/userguide/welcome.html | 2019-08-29 | 2019-08-29
| Code Deploy: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 | 1 | Complete | https://docs.aws.amazon.com/codedeploy/latest/userguide/welcome.html | 2019-08-30 | 2019-08-30
| Code Build: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 | 0.5 | Complete | https://docs.aws.amazon.com/codebuild/latest/userguide/welcome.html | 2019-09-02 | 2019-09-02
| Code Pipeline: Third party equivalent of Docker) What is it, Concepts and How it works? | 1 | 0.5 | Complete | https://docs.aws.amazon.com/codepipeline/latest/userguide/welcome.html | 2019-09-02 | 2019-09-02 | Assignment | 2019-09-03 | 2019-09-03
https://aws.amazon.com/getting-started/projects/set-up-ci-cd-pipeline/
Applying CI/CD to Projects | Usage of GIT best practices | 2 |  |  | https://datasift.github.io/gitflow/IntroducingGitFlow.html
| Jenkins for building and deployment |  |  |  | https://www.youtube.com/watch?v=p7-U1_E_j3w
| For more reference |  |  |  | https://jenkins.io/doc/
| Unit Test Cases (Python) |  |  |  | https://jeffknupp.com/blog/2013/12/09/improve-your-python-understanding-unit-testing/
| Scheduling and Orchestration Tool - Docker |  |  |  | https://www.youtube.com/watch?v=lcQfQRDAMpQ
| For more reference |  |  |  | https://docs.docker.com/get-started/
Monitoring | - Cloudwatch logging Groups - Cloudwatch agent based monitoring - KPI Definitions across services - XRay - Custom Cloudwatch Metrics | 2
Assignment : | - Consider a simple lambda function. - Create an API Gateway and Lambda that when hit, returns the message "Hello {name}, welcome to {applicationTitle}." where name is a parameter passed to this API. applicationTitle should be picked from lambda environment variable. - Implement the CICD process for this function using AWS services. Any environment variables should be set from CloudFormation. - Show the success and failure CICD scenarios. - Document the services used, the steps performed and the results. | 3
Exercise : | - The services used need to be part of a CloudFormation script that can spin up resources in any account. - Automated unit testing can involve creating custom Lambda events - All code needs to be part of a GIT repo with efficient branching strategy including code review (merge request). - Upon merging with master, latest code needs to be deployed to higher environments automatically. | 2
| Total No. of Days: | 20
Prepared By: | Rubab Naziri
Separate section for Monitoring...Cloudwatch logging groups, cloudwatch agent base monitoring, KPI defnitaions across services, Xray, Custom Cloudwatch metrics

## Shaheryar
DevOps Crash Course |  |  | Resource Name | Shaheryar
|  |  | Training Start Date | 2019-08-20
|  |  | Expected End Date | 2019-09-20
Pre Requisites: Basic knowledge of AWS Services + Python/ EC2/ VPC & VPN/ S3/ Lambda/ RDS/ CLoudTrail
Topics | Sub-Topics | Expected Duration (Days) | Time Consumed (Days) | Status (In Progress / Complete) | Reference | Start Date | End Date
Introduction | What is DevOps? | 1 | 1 | Complete | https://www.youtube.com/watch?v=PxGGeNEdb3E | 2019-08-20 | 2019-08-20
| What is CI/CD? |  |  |  | https://aws.amazon.com/devops/what-is-devops/
| The need to merge development and operations (DevOps) |  |  |  | https://enterprisersproject.com/article/2015/10/devops-case-study-rabobank-cuts-deployment-60
| Importance of DevOps in a project |  |  |  | (https://opensource.com/business/16/6/how-devops-improves-teams
Infrastructure Provisioning | AWS Accounts and Permissions (Users, Roles etc) | 1 | 1 | Complete |  | 2019-08-21 | 2019-08-21
| CloudFormation (Third party equivalents are: Chef, Puppet, Ansible) | 2 | 2 | Complete | https://docs.aws.amazon.com/AWSCloudFormation/latest/UserGuide/Welcome.html | 2019-08-21 | 2019-08-23
| 3rd party tools (Ansible, Terraform, Chef, Puppet) Understand the usecases of each services. When to used Cloudformation vs Ansible? |  |  |  | https://www.youtube.com/watch?v=OmRxKQHtDbY
| AWS AutoScaling and CloudWatch | 2 | 2 | Complete | https://docs.aws.amazon.com/AmazonCloudWatch/latest/monitoring/WhatIsCloudWatch.html | 2019-08-26 | 2019-08-28
https://docs.aws.amazon.com/autoscaling/ec2/userguide/what-is-amazon-ec2-auto-scaling.html
| AWS SNS and SES | 1 | 1 | Complete | https://docs.aws.amazon.com/ses/latest/DeveloperGuide/Welcome.html | 2019-08-27 | 2019-08-29
https://docs.aws.amazon.com/sns/latest/dg/welcome.html
CICD on AWS | Code Commit: Third party equivalent of Git) What is it, Concepts and How it works? | 1 | 1 | Complete | https://docs.aws.amazon.com/codecommit/latest/userguide/welcome.html | 2019-08-29 | 2019-08-29
| Code Deploy: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 | 1 | Complete | https://docs.aws.amazon.com/codedeploy/latest/userguide/welcome.html | 2019-08-30 | 2019-08-30
| Code Build: Third party equivalent of Jenkins) What is it, Concepts and How it works? | 1 | 0.5 | Complete | https://docs.aws.amazon.com/codebuild/latest/userguide/welcome.html | 2019-09-02 | 2019-09-02
| Code Pipeline: Third party equivalent of Docker) What is it, Concepts and How it works? | 1 | 0.5 | Complete | https://docs.aws.amazon.com/codepipeline/latest/userguide/welcome.html | 2019-09-02 | 2019-09-02
https://aws.amazon.com/getting-started/projects/set-up-ci-cd-pipeline/
Applying CI/CD to Projects | Usage of GIT best practices | 2 |  |  | https://datasift.github.io/gitflow/IntroducingGitFlow.html
| Jenkins for building and deployment |  |  |  | https://www.youtube.com/watch?v=p7-U1_E_j3w
| For more reference |  |  |  | https://jenkins.io/doc/
| Unit Test Cases (Python) |  |  |  | https://jeffknupp.com/blog/2013/12/09/improve-your-python-understanding-unit-testing/
| Scheduling and Orchestration Tool - Docker |  |  |  | https://www.youtube.com/watch?v=lcQfQRDAMpQ
| For more reference |  |  |  | https://docs.docker.com/get-started/
Monitoring | - Cloudwatch logging Groups - Cloudwatch agent based monitoring - KPI Definitions across services - XRay - Custom Cloudwatch Metrics | 2
Assignment : | - Consider a simple lambda function. - Create an API Gateway and Lambda that when hit, returns the message "Hello {name}, welcome to {applicationTitle}." where name is a parameter passed to this API. applicationTitle should be picked from lambda environment variable. - Implement the CICD process for this function using AWS services. Any environment variables should be set from CloudFormation. - Show the success and failure CICD scenarios. - Document the services used, the steps performed and the results. | 3
Exercise : | - The services used need to be part of a CloudFormation script that can spin up resources in any account. - Automated unit testing can involve creating custom Lambda events - All code needs to be part of a GIT repo with efficient branching strategy including code review (merge request). - Upon merging with master, latest code needs to be deployed to higher environments automatically. | 2
| Total No. of Days: | 20
Prepared By: | Rubab Naziri
Separate section for Monitoring...Cloudwatch logging groups, cloudwatch agent base monitoring, KPI defnitaions across services, Xray, Custom Cloudwatch metrics